## 📊 Dashboard
📊 Project Timeline Dashboard
Real-time project metrics, progress tracking & resource overview ¦ PlanoraNest.com
Overall Progress | Total Tasks | Completed | Budget Spent | Budget Remaining | Days Remaining
📋 PROJECT INFORMATION
0 | 1 |  | 2 | 3
0 | 1 |  | 2 | 3
0 | 1 |  | 2 | 3
0 | 1 |  | 2 | 3
📈 TASK STATUS BREAKDOWN
Status | Count | % of Total
Not Started
In Progress
Complete
Blocked
Delayed
TOTAL
🚩 KEY MILESTONES
Milestone | Target Date | Status | Owner | Days Until
Requirements Finalized | 2025-07-15 | Complete | PM
Design Prototype Approved | 2025-08-30 | Complete | UX Lead
Frontend Development Complete | 2025-10-15 | In Progress | Tech Lead
Backend Integration Done | 2025-11-15 | In Progress | BE Lead
QA & UAT Testing | 2025-12-01 | Not Started | QA Lead
Production Launch | 2025-12-31 | Not Started | PM
⚠️ RISK OVERVIEW
Risk Level | Count | Mitigation Status
Critical
High
Medium
Low
Formulas:
Budget Remaining = MAX(0,NETWORKDAYS(TODAY(),[Total Tasks]))

## 📋 Task Tracker
📋 Project Task Tracker & Gantt Chart
Complete Work Breakdown Structure with dependencies, critical path & automatic duration calculations
WBS ID | Task Name | Description | Department | Start Date | End Date | Duration (Days) | Predecessors | Assigned To | Status | % Complete | Actual Start | Actual End | Actual Days | Variance (Days) | Critical Path? | Comments
1.0 | Project Initiation | Kickoff, stakeholder alignment, project charter | PMO | 2025-06-01 | 2025-06-14 |  |  | Zhang Wei | Complete | 100% | 2025-06-01 | 2025-06-13 |  |  |  | Yes
1.1 | Stakeholder Interviews | Conduct 12 stakeholder discovery sessions | PMO | 2025-06-01 | 2025-06-07 |  |  | Li Na | Complete | 100% | 2025-06-01 | 2025-06-06 |  |  |  | Yes
1.2 | Project Charter Draft | Write and circulate project charter for approval | PMO | 2025-06-08 | 2025-06-14 |  | 1.1 | Zhang Wei | Complete | 100% | 2025-06-07 | 2025-06-13 |  |  |  | Yes
2.0 | Requirements Gathering | User stories, functional & non-functional requirements | Product | 2025-06-15 | 2025-07-15 |  | 1.0 | Chen Xiao | Complete | 100% | 2025-06-15 | 2025-07-14 |  |  |  | Yes
2.1 | User Research | User interviews, surveys, competitive analysis | UX | 2025-06-15 | 2025-06-30 |  | 1.2 | Wang Fang | Complete | 100% | 2025-06-15 | 2025-07-01 |  |  |  | No
2.2 | Functional Specs | Document all functional requirements & user flows | Product | 2025-07-01 | 2025-07-10 |  | 2.1 | Chen Xiao | Complete | 100% | 2025-07-01 | 2025-07-09 |  |  |  | No
2.3 | Technical Specs | API design, data model, integration requirements | Engineering | 2025-07-05 | 2025-07-15 |  | 2.1 | Zhao Lei | Complete | 100% | 2025-07-05 | 2025-07-15 |  |  |  | No
3.0 | Design Phase | UI/UX design, prototyping & design system | UX | 2025-07-16 | 2025-09-15 |  | 2.0 | Wang Fang | In Progress | 85% | 2025-07-16 |  |  |  |  | Yes
3.1 | Wireframes | Low-fidelity wireframes for all 24 screens | UX | 2025-07-16 | 2025-08-10 |  | 2.3 | Wang Fang | Complete | 100% | 2025-07-16 | 2025-08-09 |  |  |  | No
3.2 | High-Fidelity Mockups | Pixel-perfect designs for all screens | UX | 2025-08-11 | 2025-09-05 |  | 3.1 | Liu Yang | In Progress | 90% | 2025-08-11 |  |  |  |  | No
3.3 | Design System | Component library, tokens, responsive breakpoints | UX | 2025-08-15 | 2025-09-15 |  | 3.2 | Wang Fang | In Progress | 70% | 2025-08-15 |  |  |  |  | No
3.4 | Prototype Testing | Usability testing with 15 participants | UX | 2025-09-01 | 2025-09-14 |  | 3.2 | Liu Yang | Not Started | 0% | [5 empty] | No
4.0 | Frontend Development | React/Next.js implementation of all screens | Engineering | 2025-09-01 | 2025-11-15 |  | 3.0 | Zhao Lei | In Progress | 35% | 2025-09-01 |  |  |  |  | Yes
4.1 | Component Development | Build all reusable UI components | Engineering | 2025-09-01 | 2025-10-15 |  | 3.3 | Zhao Lei | In Progress | 50% | 2025-09-01 |  |  |  |  | No
4.2 | Page Assembly | Assemble pages, routing, state management | Engineering | 2025-10-01 | 2025-10-31 |  | 4.1 | Sun Yue | Not Started | 25% | 2025-10-01 |  |  |  |  | No
4.3 | API Integration | Connect frontend to all backend endpoints | Engineering | 2025-10-15 | 2025-11-10 |  | 4.1 | Zhao Lei | Not Started | 0% | [5 empty] | No
4.4 | Performance Optimization | Lighthouse score > 90, bundle optimization | Engineering | 2025-11-01 | 2025-11-15 |  | 4.2,4.3 | Sun Yue | Not Started | 0% | [5 empty] | No
5.0 | Backend Development | API, database, auth, infrastructure | Engineering | 2025-09-15 | 2025-11-30 |  | 2.0 | Huang Wei | In Progress | 30% | 2025-09-15 |  |  |  |  | Yes
5.1 | Database Schema | Design & implement PostgreSQL schema | Engineering | 2025-09-15 | 2025-09-30 |  | 2.3 | Huang Wei | Complete | 100% | 2025-09-15 | 2025-09-29 |  |  |  | No
5.2 | API Development | RESTful API endpoints, GraphQL layer | Engineering | 2025-10-01 | 2025-11-15 |  | 5.1 | Huang Wei | In Progress | 40% | 2025-10-01 |  |  |  |  | No
5.3 | Authentication System | OAuth2.0, JWT, role-based access control | Engineering | 2025-10-15 | 2025-11-05 |  | 5.1 | Ma Jing | In Progress | 25% | 2025-10-15 |  |  |  |  | No
5.4 | CI/CD Pipeline | GitHub Actions, Docker, AWS deployment | DevOps | 2025-10-01 | 2025-10-31 |  | 5.1 | Zhou Tao | In Progress | 60% | 2025-10-01 |  |  |  |  | No
6.0 | Quality Assurance | Testing, bug fixing & UAT | QA | 2025-11-16 | 2025-12-15 |  | 4.0,5.0 | Xu Jing | Not Started | 0% | [5 empty] | Yes
6.1 | Test Plan Creation | Test cases, test data, automation scripts | QA | 2025-11-16 | 2025-11-25 |  | 4.4,5.4 | Xu Jing | Not Started | 0% | [5 empty] | No
6.2 | Integration Testing | End-to-end integration test execution | QA | 2025-11-26 | 2025-12-05 |  | 6.1 | Xu Jing | Not Started | 0% | [5 empty] | No
6.3 | UAT | User acceptance testing with stakeholders | QA | 2025-12-06 | 2025-12-12 |  | 6.2 | Zhang Wei | Not Started | 0% | [5 empty] | No
6.4 | Bug Fixes | Critical & high-priority bug resolution | Engineering | 2025-12-01 | 2025-12-15 |  | 6.2 | Zhao Lei | Not Started | 0% | [5 empty] | No
7.0 | Launch & Closeout | Production deployment & project retrospective | PMO | 2025-12-16 | 2025-12-31 |  | 6.0 | Zhang Wei | Not Started | 0% | [5 empty] | Yes
7.1 | Production Deployment | Go-live deployment & smoke testing | DevOps | 2025-12-16 | 2025-12-19 |  | 6.3,6.4 | Zhou Tao | Not Started | 0% | [5 empty] | No
7.2 | Post-Launch Monitoring | Monitor KPIs, error rates, user feedback for 2 weeks | Engineering | 2025-12-20 | 2025-12-28 |  | 7.1 | All Team | Not Started | 0% | [5 empty] | No
7.3 | Retrospective | Project retrospective & lessons learned documentation | PMO | 2025-12-29 | 2025-12-31 |  | 7.2 | Zhang Wei | Not Started | 0% | [5 empty] | No
📊 TASK SUMMARY
| TOTAL TASKS: |  | COMPLETED: |  | IN PROGRESS: |  | BLOCKED: |  | AVG PROGRESS:
Formulas:
Duration (Days) = IF(AND([Start Date]<>"",[End Date]<>""),NETWORKDAYS([Start Date],[End Date]),"")
Actual Days = IF(AND([Actual Start]<>"",[Actual End]<>""),NETWORKDAYS([Actual Start],[Actual End]),IF(AND([Actual Start]<>"",[Actual End]=""),NETWORKDAYS([Actual Start],TODAY()),""))

## 💰 Budget & Resources
💰 Budget & Resource Allocation
Track all project resources, budget allocation, actual spend & cost variance analysis
Resource ID | Resource Name | Type | Department | Rate ($/hr or $/day) | Unit | Allocated Hours/Days | Budget ($) | Actual ($) | Variance ($) | Variance % | Utilization % | Assigned Tasks | Notes
RES-01 | Zhang Wei | Human | PMO | 75 | hr | 480 | [5 empty] | 1.2,1.3,7.3 | Senior PM
RES-02 | Li Na | Human | PMO | 55 | hr | 320 | [5 empty] | 1.1
RES-03 | Wang Fang | Human | UX | 65 | hr | 520 | [5 empty] | 2.1,3.1,3.3 | UX Lead
RES-04 | Liu Yang | Human | UX | 50 | hr | 480 | [5 empty] | 3.2,3.4
RES-05 | Zhao Lei | Human | Engineering | 80 | hr | 640 | [5 empty] | 2.3,4.1,4.3,6.4 | Tech Lead
RES-06 | Sun Yue | Human | Engineering | 60 | hr | 480 | [5 empty] | 4.2,4.4
RES-07 | Huang Wei | Human | Engineering | 70 | hr | 560 | [5 empty] | 5.1,5.2 | BE Lead
RES-08 | Ma Jing | Human | Engineering | 55 | hr | 400 | [5 empty] | 5.3
RES-09 | Zhou Tao | Human | DevOps | 75 | hr | 360 | [5 empty] | 5.4,7.1 | DevOps Lead
RES-10 | Xu Jing | Human | QA | 60 | hr | 400 | [5 empty] | 6.1,6.2,6.3 | QA Lead
RES-11 | Chen Xiao | Human | Product | 70 | hr | 320 | [5 empty] | 2.0,2.2 | Product Mgr
RES-12 | AWS Cloud | Infrastructure | DevOps | 5000 | mo | 6 | [6 empty] | $5k/month for 6 months
RES-13 | Figma Enterprise | Software | UX | 75 | mo | 7 | [6 empty] | Per seat/month × 3 seats
RES-14 | GitHub Enterprise | Software | Engineering | 42 | mo | 7 | [6 empty] | Per seat/month × 8 seats
RES-15 | Testing Devices | Equipment | QA | 0 | one | 1 | 3000 | [5 empty] | Mobile + tablet test lab
RES-16 | SSL Certificate | Software | DevOps | 0 | one | 1 | 1500 | [5 empty] | Wildcard cert
RES-17 | Analytics Tool | Software | Product | 199 | mo | 6 | [6 empty] | Mixpanel/Amplitude
RES-18 | Training Budget | Service | PMO | 0 | one | 1 | 5000 | [5 empty] | Team upskilling
RES-19 | Contingency | Reserve | PMO | 0 | one | 1 | 18000 | [5 empty] | 10% contingency
RES-20 | Content Writer | Human | Marketing | 45 | hr | 160 | [6 empty] | Launch content
📊 BUDGET SUMMARY
| TOTAL BUDGET: |  | TOTAL ACTUAL: |  | VARIANCE: |  | CONTINGENCY REMAINING:
📊 BUDGET BY DEPARTMENT
| Department | Budget ($) | Actual ($) | Variance ($) | Variance %
PMO
Product
UX
Engineering
DevOps
QA
Marketing

## 🚩 Risk Register
🚩 Project Risk Register
Identify, assess & track project risks with probability-impact matrix and mitigation planning
Risk ID | Risk Description | Category | Probability | Impact | Risk Score | Risk Level | Mitigation Strategy | Owner | Status | Date Identified | Last Reviewed
R-01 | Key developer departure mid-project | Resource | Medium | Critical |  |  | Cross-train developers, maintain thorough documentation, identify backup resources | PM | Monitored | 2025-06-01 | 2025-09-15
R-02 | Third-party API rate limit changes | Technical | Medium | High |  |  | Implement caching layer, negotiate enterprise SLA with vendor, build fallback queue | Tech Lead | Active | 2025-06-15 | 2025-10-01
R-03 | Scope creep from stakeholder requests | Scope | High | High |  |  | Formal change control process, weekly stakeholder reviews, prioritized backlog | PM | Active | 2025-06-01 | 2025-09-20
R-04 | Design approval delays from client | Schedule | High | Medium |  |  | Set clear approval SLAs in contract, schedule buffer days, parallel review tracks | PM | Monitored | 2025-07-01 | 2025-10-15
R-05 | Database performance under load | Technical | Medium | High |  |  | Load testing from sprint 1, query optimization, read replicas, caching strategy | BE Lead | Active | 2025-07-15 | 2025-11-01
R-06 | Browser compatibility issues | Technical | Low | Medium |  |  | Browserstack testing, progressive enhancement, polyfill strategy, supported browser matrix | QA Lead | Monitored | 2025-08-01 | 2025-11-15
R-07 | Budget overrun on cloud infrastructure | Financial | Medium | Medium |  |  | AWS budget alerts, auto-scaling limits, reserved instances, monthly cost review | DevOps | Active | 2025-06-01 | 2025-10-01
R-08 | Security vulnerability discovered late | Security | Low | Critical |  |  | SAST/DAST in CI pipeline, quarterly pen testing, dependency scanning, OWASP checklist | Tech Lead | Monitored | 2025-06-01 | 2025-11-01
R-09 | UAT reveals major UX issues | Quality | Medium | High |  |  | Early prototype testing with real users, iterative design, usability benchmarks | UX Lead | Monitored | 2025-08-15 | 2025-11-20
R-10 | Launch date conflict with marketing event | Schedule | Low | Low |  |  | Coordinate with marketing team quarterly, maintain flexible launch window options | PM | Monitored | 2025-09-01 | 2025-12-01
R-11 | Data migration failure | Technical | Low | Critical |  |  | Dry-run migrations, rollback plan, data validation checks, backup before each migration | BE Lead | Active | 2025-10-01 | 2025-11-15
R-12 | Vendor lock-in with proprietary service | Strategic | Low | Medium |  |  | Abstract vendor interfaces, evaluate open-source alternatives, maintain exit strategy | Tech Lead | Monitored | 2025-06-15 | 2025-10-15
📊 RISK SUMMARY BY LEVEL
| Risk Level | Count | % of Total
Critical
High
Medium
Low

## 📈 Monthly Progress
📈 Monthly Progress & Velocity Tracker
Track month-over-month project progress, team velocity, budget burn & risk trends
Month | Planned Tasks | Completed Tasks | Completion Rate | Planned Budget ($) | Actual Spend ($) | Budget Variance ($) | Risks Open | Risks Closed | Team Velocity | Cumulative Progress %
2025-06 | 8 | 8 |  | 18000 | 16500 |  | 5 | 0 | 32
2025-07 | 10 | 10 |  | 25000 | 23200 |  | 7 | 2 | 38
2025-08 | 12 | 11 |  | 28000 | 27100 |  | 9 | 3 | 35
2025-09 | 14 | 12 |  | 32000 | 30100 |  | 10 | 2 | 42
2025-10 | 16 | 8 |  | 35000 |  |  | 11 | 1 | 0
2025-11 | 14 | 0 |  | 30000 |  |  | 8 | 0 | 0
2025-12 | 10 | 0 |  | 22000 |  |  | 5 | 0 | 0
TOTAL

## 📖 Instructions
How to Use: Project Timeline & Gantt Chart (Professional Edition)
Overview
This is a comprehensive multi-dimensional project management template with 5 interconnected sheets. It combines task tracking (WBS + Gantt), resource budgeting, risk management, and monthly progress analytics — all linked through formulas for real-time project intelligence. Every key metric flows automatically to the Dashboard.
Project Setup
Go to 📊 Dashboard and fill in your project name, dates, budget total, and manager info.
Review the pre-populated sample data to understand the template structure.
Adjust the sample milestones to match your project timeline.
Task Planning (WBS)
Navigate to 📋 Task Tracker — this is your Work Breakdown Structure (WBS).
Enter each task with a WBS ID, name, description, and department.
Set Start Date and End Date — the Duration column auto-calculates using NETWORKDAYS().
Define Predecessors by referencing other WBS IDs to build dependency chains.
Mark tasks on the Critical Path as 'Yes' to highlight them in red across the row.
Use the dropdown menus for Status and Department to maintain data consistency.
Resource & Budget Management
Go to 💰 Budget & Resources to plan all project costs.
Enter each human resource with their hourly rate and allocated hours — budget auto-calculates.
Add infrastructure, software licenses, equipment, and services.
Track actual spend vs budget — variance columns highlight over/under automatically.
The contingency reserve (10%) is built-in; monitor it on the budget summary row.
Department budget breakdown uses SUMIF to aggregate costs by team.
Risk Management
Open 🚩 Risk Register to identify and assess project risks.
For each risk, select Probability and Impact from dropdowns.
The Risk Score auto-calculates (P×I matrix) and Risk Level is derived automatically.
Use the conditional formatting (green→yellow→red) to prioritize mitigation efforts.
Update Status as risks evolve: Active → Monitored → Resolved → Closed.
Review risk trends on the 📈 Monthly Progress sheet alongside budget data.
Progress Tracking
📈 Monthly Progress captures month-over-month velocity and budget burn.
Enter actual completed tasks and spend each month.
The Cumulative Progress % column tracks overall project trajectory.
Use the built-in line chart to visualize progress toward your targets.
Compare planned vs actual metrics to identify schedule or budget slippage early.
Real-Time Dashboard
📊 Dashboard aggregates data from ALL other sheets automatically.
KPI cards show Overall Progress (%), Total Tasks, Completed, Budget metrics, and Days Remaining.
Task Status Breakdown uses COUNTIF across the Task Tracker.
Milestones section shows upcoming dates and auto-calculates Days Until.
Risk Overview summarizes risk levels from the Risk Register.
Key Formulas Reference
= NETWORKDAYS(start, end) — Calculates working days between two dates (excludes weekends)
= COUNTIF(range, criteria) — Counts cells matching a condition (e.g., status = 'Complete')
= SUMIF(range, criteria, sum_range) — Sums values matching a department or category
= IF(condition, true_val, false_val) — Conditional logic for variance, status, levels
= MATCH + INDEX — Used in Risk Score matrix (Probability × Impact)
= Data Validation dropdowns — Ensure data consistency with predefined options
= Conditional Formatting — Auto-color cells based on values (data bars, color scales, rules)
= SUM / AVERAGE / MAX / MIN — Standard aggregation across all sheets
Pro Tips for Professional Project Management
💡 Update the Task Tracker weekly and review the Dashboard on Monday mornings — 15 minutes saves hours of confusion.
💡 Use the Critical Path column to identify tasks that cannot slip without delaying the entire project.
💡 Set calendar reminders to update Actual Spend in Budget & Resources at least bi-weekly.
💡 For the Risk Register, review and update risk status during every sprint retrospective.
💡 Export the Monthly Progress chart to include in stakeholder status reports.
💡 Customize the dropdown lists (Data → Data Validation) to match your organization's departments and categories.
💡 Protect sheets (Review → Protect Sheet) once your project data is finalized to prevent accidental edits.
💡 Use Filter (Ctrl+Shift+L) on the Task Tracker to focus on specific departments, statuses, or assignees.

## ℹ️ About
About: Project Timeline & Gantt Chart (Professional Edition)
Template Name: | Project Timeline & Gantt Chart — Professional Edition
Category: | Business & Management / Project Management
Version: | 2.0 — Multi-Sheet Professional Edition
Last Updated: | June 21, 2026
Complexity Level: | Advanced — 5 interconnected data sheets + Dashboard + auto-calculations
Formula Count: | 200+ built-in formulas (NETWORKDAYS, COUNTIF, SUMIF, IF, MATCH, nested logic)
Interactive Elements: | Data validation dropdowns, conditional formatting, data bars, color scales, charts
Compatibility: | Microsoft Excel 2010+, Google Sheets, LibreOffice Calc (minor formatting variations)
License: | MIT — Free for personal & commercial use
Website: | https://planoranest.com/
Sheet Structure
📊 Dashboard — Real-time KPIs, status breakdown, milestones, risk overview
📋 Task Tracker — 30-task WBS with Gantt data, dependencies, critical path, auto-duration
💰 Budget & Resources — 20 resources across departments with budget vs actual and variance
🚩 Risk Register — 12 risks with probability-impact matrix, scoring, and mitigation
📈 Monthly Progress — 7-month velocity tracker with cumulative progress chart
📖 Instructions — Complete step-by-step tutorial and formula reference
ℹ️ About — This sheet
Keywords / SEO Tags
project timeline template, project management excel, gantt chart template, WBS template, project budget tracker, risk register excel, task tracker spreadsheet, critical path analysis, project dashboard, resource allocation template, monthly progress tracker, team velocity, earned value management, project portfolio, PlanoraNest
(c) 2026 PlanoraNest. All rights reserved. ¦ https://planoranest.com/